## Estimates
Days per task |  |  |  |  | Aggregate per milestone
Size | lower_est | upper_est |  |  | Row Labels | Sum of lower_est | Sum of upper_est
Tiny | 0.1 | 0.5 |  |  | v0.2 | 1.5 | 3
Small | 0.5 | 1 |  |  | v0.3 | 9 | 21
Medium | 1 | 2 |  |  | Grand Total | 10.5 | 24
Large | 2 | 5
X-Large | 5 | 100
Tasks per milestone
MS | count | size | lower_est | upper_est
v0.2 | 3 | Small | 1.5 | 3
v0.3 | 2 | Small | 1 | 2
v0.3 | 2 | Medium | 2 | 4
v0.3 | 3 | Large | 6 | 15

## Likely Available Dates
Available dates
1 | 2022-10-10
2 | 2022-10-11 | Start v0.2
3 | 2022-10-12 | Earliest finish v0.2
4 | 2022-10-13
5 | 2022-10-14 |  | Latest Finish v0.2
6 | 2022-10-24 |  | 1
7 | 2022-10-25 |  | 2
8 | 2022-10-26 |  | 3
9 | 2022-10-27 |  | 4
10 | 2022-10-28 |  | 5
11 | 2022-10-31 |  | 6
12 | 2022-11-08 | Earliest finish v0.3 | 7
13 | 2022-11-09 |  | 8
14 | 2022-11-10 |  | 9
15 | 2022-11-11 |  | 10
16 | 2022-11-21 |  | 11
17 | 2022-11-22 |  | 12
18 | 2022-11-23 |  | 13
19 | 2022-11-24 |  | 14
20 | 2022-11-25 |  | 15
21 | 2022-12-05 |  | 16
22 | 2022-12-06 |  | 17
23 | 2022-12-07 |  | 18
24 | 2022-12-08 |  | 19
25 | 2022-12-09 |  | 20
26 | 2022-12-19 |  | Latest Finish v0.3